## BOQ Data
Code | Description | Quantity | Unit | Unit Cost | Duration (days) | Predecessors | Total Cost
A001 | Site Clearing and Preparation | 1500 | m² | 5.5 | 5 |  | 8250
A002 | Excavation and Earthwork | 800 | m³ | 25 | 7 | A001 | 20000
A003 | Foundation Concrete Works | 120 | m³ | 85 | 10 | A002 | 10200
A004 | Reinforcement Steel for Foundation | 15 | tons | 1200 | 8 | A003 | 18000
A005 | Ground Floor Slab Concrete | 100 | m³ | 90 | 6 | A003 | 9000
A006 | Ground Floor Slab Reinforcement | 12 | tons | 1300 | 5 | A004 | 15600
A007 | Column Concrete (Ground to 2nd Floor) | 80 | m³ | 95 | 12 | A005 | 7600
A008 | Column Reinforcement | 8 | tons | 1350 | 10 | A006 | 10800
A009 | Beam Concrete (Each Floor) | 75 | m³ | 92 | 8 | A007 | 6900
A010 | Beam Reinforcement | 7.5 | tons | 1320 | 7 | A008 | 9900
A011 | Slab Concrete (Each Floor) | 85 | m³ | 88 | 6 | A009 | 7480
A012 | Slab Reinforcement | 8.5 | tons | 1280 | 5 | A010 | 10880
A013 | Brick Masonry Works | 450 | m² | 12.5 | 15 | A011 | 5625
A014 | Plastering and Finishing | 1200 | m² | 8.5 | 12 | A012 | 10200
A015 | Painting and Decoration | 950 | m² | 6.75 | 8 | A013 | 6412.5